## Sheet1
Group Name | Team Members | March |  |  |  | April |  |  |  | May |  |  |  | June
|  | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | Notes
WP 1: Leading Manager: Wu Xiulin
Task 1.1: Choose the technologies to be used for the front end, the back end, the API for Machine Learning | Wu Xiulin
Task 1.2: Making plan and writing relevant documents for the project, such as team agreement, project proposal | All Members
Task 1.3: Design basic database model | Wu Xiulin, Zhengsheng
Task 1.4: Design basic websites of the project, with front end and back end corporation | Yadi, Zhengzhi
Task 1.5: Add complex functions to the websites, with customer group recommendation | All Members
Task 1.6: Make sure all the works work well | All Members
Task 1.7: Testing and find the shortages of the project | All Members
WP 2: Customer Manager: Zhi Zheng
Task 2.1:Collect the functional user requirements | Zhi Zheng
Task 2.2:Collect the non-functional user requirements | Zhi Zheng
Task 2.3:Come out with user requirements | All Members
Task 2.4:Communicate with the professor and other users | All Members
Task 2.5:Do the acceptance test | All Members
Task 2.6:Test the work package implementation | All Members
WP3: Code Manager: Yang Yadi
Task 3.1:Start to write code according to the requirements of other group analysis and determine the basic framework | Yang Yadi
Task 3.2:Back end team members write database and Spring framework | Zhengsheng, Xiulin
Task 3.3:Front end team members make web pages according to the requirements of each group | Yadi, Zheng Zhi
Task 3.4 All members use some ML and IR technology to improve the competitiveness of the website | All Members
Task 3.5:Modify the problems found by other groups, beautify the page design and complete the final version | All Members
WP4: Maintenance Manager: Li Zhensheng
Task 4.1: Writing the project plan/proposal | All Members
Task 4.2: Organizing presentations demos | Yadi, Zheng Zhi
Task 4.3: Testing the project | Zhengsheng, Xiulin
Task 4.4: Writing user’s guide, system document and other relevant documents | All Members
Deliverable
Milestone